## Slide 1: online component repository PROJECT PLAN AND REQUIREMENTS
CTD401 – Group 1

## Slide 2: Team members
VLADIMIR DJUKANOVIC – PROJECT MANAGER
CRISTIAN CAPOZUCCO
BASTIEN DELBOUYS
ALEKSANDAR MATOVIC
MOHAMMED ABDI
OSKAR PALMGREN

## Slide 3: PROJECT DESCRIPTION​
The project regards a case study of an online software component repository​
There are two type of users:​
Normal users (browse and search components and so on)​
Admins (add/remove components and so on)​
The system must be realized through a component-based architecture

## Slide 4: summary
Communication & synchronization
Activities
Deliverables
Risks

## Slide 5: Communication & Synchronization
Meetings at least once a week to make the point of the situation and to plan future working
Microsoft Teams will be used to communicate and to share files and links
Github will be used to host the project
Trello to coordinate work activites

## Slide 6: Activities
ID | Description​ | Effort (person hours)
1 | Project plan​ agreement | 3
2 | Write project plan | 14
3 | Project plan presentation | 5
4 | UML diagram design | 9
5 | UI agreement | 5

## Slide 7: Activities
ID | Description​ | Effort (person hours)
6 | Sketch UI | 15
7 | Write design document (first version) | 24
8 | Initial implementation of C# application | 90
9 | Testing | 40
10 | Write design document (final version) | 78

## Slide 8: Activities
ID | Description​ | Effort (person hours)
11 | Further implementation of C# | 71
12 | Testing | 60
13 | Write final report | 56

## Slide 9: Deliverables
Description​ | Deadline​
Project plan​ | 2018-09-27​
Design Document​ | 2018-10-18​
Prototype implementation​ | 2018-10-29​
Project Analysis​ | 2018-11-08​
Peer and Self Assessment​ | 2018-11-11​

## Slide 10: Risks
Bad requirements engineering affects:
  Design
  Implementation
  Testing
The group members never worked together
Members’ skillset